## Test Plan
Test Plan
Product Name |  | PublicMarketBd | Module | User Profile | Author | Nurul Afsar | Version | 1
1 | Test Plan ID | PMBD_UP01
2 | Introduction | This document was created as a test plan for an online market system named PublicMarketBD. publicmarket.com.bd is a platform on which you can buy and sell almost everything. It provides certain services to its users so that they can use this website as a common zone for selling or purchasing their lawful or permitted products/contents. The test plan mainly discusses user management, including new user sign-up, sign-in, changing passwords, etc. This document describe approaches and methodologies that will apply to the unit, integration and system testing of the "https://publicmarket.com.bd/". It includes the test items, references, features to be tested, features not to be tested,test approaches, entry and exit criteria, roles and responsibilities, schedule , trainning, test environment etc. This document has clearly identified what the test deliverables will be, and what is deemed in and out of scope.
3 | Test Items | User Management
4 | References | Requirements, Prototypes
5 | Features to be tested | Sign-up, Sign-In, Change Password, Update Profile, Forgot Password
6 | Features not to be tested | Dashboard, My Account, My Applied Jobs, Add Phone
7 | Test Approach | Test runs are conducted for each test case listed in MS Excel. The tester will execute the tests in MS Excel and mark each case as Passed / Failed / Not Executed / Out of scope. Test cases marked as failed will be documented in MS Excel as Bug Report. The tester should leave comments on any critical issues found and attach a snapshot. Once completed, the Test Manager will review the test cases in MS Excel and subsequently report to the concerned team members.
8 | Entry Criteria
9 | Exit Criteria
10 | Suspension Criteria
11 | Roles and Resposibilities | Nurul Afsar- Junior SQA
12 | Schedule
13 | Trainning | SQA and Cyber Security, IT Trainning BD
14 | Test Environment
15 | Test Deliverables | Mind Maps, Test report, Test cases, bug report, Test metrics
16 | Approvals
17 | Glossary

## Report
Test Case Report
Project Name | PublicMarket Bd
Module Name | User Profile |  |  |  |  | Total No. | Status | Result :
Test Case Version | 1 |  |  |  |  | 38 | PASS
Written By | Nurul Afsar |  |  |  |  | 1 | FAIL
Executed By | Nurul Afsar |  |  |  |  | 7 | Not Executed | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 38 | 1 | 7 | 0 | 46
Grand Total | 38 | 1 | 7 | 0 | 46
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## TestCase
Product Name |  | publicmarketbd | TC Start Date | 26/03/2023 | TC Execution Start Date | 17/04/2023 |  |  |  |  | TEST CASE
Module Name |  | User Profile | TC End Date | 2023-10-04 | TC Execution End Date | 18/04/2023 |  |  |  |  | PASS | 38
Epic |  |  | Test Case Developed By | Nurul Afsar | Browser (tested) | Yes |  |  |  |  | FAIL | 1
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | No |  |  |  |  | Not Executed | 7
Test Executed by |  | Nurul Afsar | [8 empty] | Out of Scope | 0
[11 empty] | TOTAL | 46
#SL | Module | Features | Type of Testing | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  |  | Browser Compatibility Testing | Running the site in various browsers to test | Should run in different browsers | Found as per expectation | Chrome Mozilla Firefox Microsoft Edge Safari | 1. Goto different browsers 2. search "publicmarketbd" 3. Click on the site |  |  | Passed
2 | User Account | Register | UI Testing | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 4. Check the font, text color and style |  |  | Passed
4 |  |  |  | Verifying placeholders text for proper input fields | Proper placeholder text should be present | Found as per expectation | N/A | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Check the inputs with proper placeholder |  |  | Passed
5 |  |  |  | Checking by hovering over the link and button | Change the color over the links and button | Found as per expectation | N/A | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Hover over every links and button |  |  | Passed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Check alignment of the fields |  |  | Passed
7 |  |  |  | Checking password visible icon | A password visible icon should appear in both password and confirm password field | Found as per expectation | N/A | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Check eye icon in password field |  |  | Passed
8 |  |  | Functional Testing | Checking that after clicking a division in the division list, a list containing the district name is displayed | Should be displayed all districts under the selected division | Found as per expectation | Division: Dhaka | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division |  |  | Passed
Passed
|  |  |  | Signing up by keeping mandatory fields blank | An error message should be dispalyed | Found as per expectation | N/A | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5.Keep mandatory fields blank |  |  | Passed
9 |  |  |  | Verify phone number field by entering alphabets | Should not accept the provided input | Found as per expectation | abCDe | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input "abCDe" in the Phone Number field |  |  | Passed
10 |  |  |  | Verify phone number field by entering special characters | Should not accept the provided input | Found as per expectation | $$@@** | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input "$$@@**" in the Phone Number field |  |  | Passed
11 |  |  |  | Verify phone number field by adding only the spaces | Should not accept the provided input | Found as per expectation | (space) | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input "space" in the Phone Number field |  |  | Passed
12 |  |  |  | Verify by entering less number than the actual phone number | An error message should be dispalyed | Found as per expectation | 1834 | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input "01234" in the Phone Number field |  |  | Passed
13 |  |  |  | Verify phone number field by entering invalid phone number | An error message should be dispalyed | Found as per expectation | 82765834587 | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input "82765834587" in the Phone Number field |  |  | Passed
14 |  |  |  | Checking if the password field is encrypted by default | It Should be unreadable and as a series of dot(.) | Found as per expectation | 12abc | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input "12abc" in the Password field |  |  | Passed
15 |  |  |  | Checking if the password field has a minimum length | Password should be at least 8 characters | Found as per expectation with a validation message | 12345 | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input "12345" in the Password field |  |  | Passed
16 |  |  |  | Checking if the password field has a maximum length | Maximum password length should be defined | No maximum limit | 0123456789a0123456789b0123456789c0123456789d0123456789e0123456789f0123456789g0123456789h0123456789i0123456789j0123456789k0123456789l0123456789m0123456789n0123456789o0123456789p0123456789q0123456789r0123456789s0123456789t0123456789u0123456789v0123456789w0123456789x0123456789y0123456789z0123456789A0123456789B0123456789C0123456789D0123456789E0123456789F0123456789G0123456789a0123456789b0123456789c0123456789d0123456789e0123456789f0123456789g0123456789h0123456789i0123456789j0123456789k0123456789l0123456789m0123456789n0123456789o0123456789p0123456789q0123456789r0123456789s0123456789t0123456789u0123456789v0123456789w0123456789x0123456789y0123456789z0123456789A0123456789B0123456789C0123456789D0123456789E0123456789F0123456789G9874560123456789a0123456789b0123456789c0123456789d0123456789e0123456789f0123456789g0123456789h0123456789i0123456789j0123456789k0123456789l0123456789m0123456789n0123456789o0123456789p0123456789q0123456789r0123456789s0123456789t0123456789u0123456789v0123456789w0123456789x0123456789y0123456789z0123456789A0123456789B0123456789C0123456789D0123456789E0123456789F0123456789G | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input "0123456789a0123456789b0123456789c0123456789d0123456789e0123456789f0123456789g0123456789h0123456789i0123456789j0123456789k0123456789l0123456789m0123456789n0123456789o0123456789p0123456789q0123456789r0123456789s0123456789t0123456789u0123456789v0123456789w0123456789x0123456789y0123456789z0123456789A0123456789B0123456789C0123456789D0123456789E0123456789F0123456789G0123456789a0123456789b0123456789c0123456789d0123456789e0123456789f0123456789g0123456789h0123456789i0123456789j0123456789k0123456789l0123456789m0123456789n0123456789o0123456789p0123456789q0123456789r0123456789s0123456789t0123456789u0123456789v0123456789w0123456789x0123456789y0123456789z0123456789A0123456789B0123456789C0123456789D0123456789E0123456789F0123456789G9874560123456789a0123456789b0123456789c0123456789d0123456789e0123456789f0123456789g0123456789h0123456789i0123456789j0123456789k0123456789l0123456789m0123456789n0123456789o0123456789p0123456789q0123456789r0123456789s0123456789t0123456789u0123456789v0123456789w0123456789x0123456789y0123456789z0123456789A0123456789B0123456789C0123456789D0123456789E0123456789F0123456789G" in the Password and Confirm password field 6. Enter Register button |  |  | Failed
17 |  |  |  | Checking the visibility of the password by clicking the visible icon | Password should be readable | Found as per expectation | 123456asdf | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input "123456asdf" in the Password field 6. Click on Eye icon in the password field |  |  | Passed
18 |  |  |  | Checking whether the verification code has been sent | A Six digit verification code has to be sent to the registered phone number | Found as per expectation | Phone Number: 01304405800 Password: 12345678 Confirm Password: 12345678 | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input all required field 6. Click on register |  |  | Passed
|  |  |  | Checking confirmation message sent to the registered phone number | A confirmation message should be sent | Found as per expectation | Phone Number: 01304405800 Password: 12345678 Confirm Password: 12345678 | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input all required field 6. Click on register 7. Input the Verification code sent to the registered phone number |  |  | Passed
|  |  |  | Verifying new register with existing phone number | Should display an error message | Found as per expectation | Phone Number: 01304405800 Password: 00000000 Confirm Password: 00000000 | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input all required field 6. Click on register 7. Input the Verification code sent to the registered phone number |  |  | Passed
19
20 |  |  | Usability Testing | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | Confirm Password: 12345678 | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Copy paste text in every field |  |  | Passed
21 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Enter tab in every field |  |  | Passed
22 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | Input Enter in every field | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at the top navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Enter enter in every field |  |  | Passed
23 |  | Log In | Functional Testing | Keeping phone number and password field blank | Should not allow user to login and display an error messeage | Found as per expectation | N/A | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at the top navigation bar 3. Keep all field blank 4. Click on "Login" button |  |  | Passed
24 |  |  |  | Checking if the data in password is encrypted | Should be encrypted with dot | Found as per expectation | jony123 | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at the top navigation bar 3. Input password in the Password field |  |  | Passed
25 |  |  |  | Checking login with invalid phone number | Should not allow user to login and display an error messeage | Found as per expectation | Phone Number: 01000000000 Password: 123456 | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at the top navigation bar 3. Input invalid phone number and password 4. Click on "Login" button |  |  | Passed
26 |  |  |  | Checking login with valid phone number and wrong password | Should not allow user to login and display an error messeage | Found as per expectation | Phone Number: 01304405800 Password: jane@2222 | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at the top navigation bar 3. Input valid phone number and wrong password 4. Click on "Login" button |  |  | Passed
|  |  |  | Checking phone number field by typing characters | Should not allow to typing in the field | Found as per expectation | asdfghij | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at the top navigation bar 3. Input characters in the phone number field |  |  | Passed
|  |  |  | Verifying whether the login screen is responsive to different screen resolutions and devices. | It should be adjustable to different screen resolutions and devices. | Found as per expectation | N/A |  |  |  | Passed
27 |  |  |  | Verifying if the forgot password link is working correctly | It should be landed on the correct page | Found as per expectation | N/A | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at the top navigation bar 3. Click on forgot password |  |  | Passed
28 |  |  |  | Verifying if the OTP of forgot password is sent to the user's phone number | An OTP should sent to user's registered phone number | Found as per expectation | N/A | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at the top navigation bar 3. Click on forgot password 4. Input valid user phone number 5. click on Submit button |  |  | Passed
29 |  |  |  | Checking by inputting the wrong OTP of forgot password | An error message should be dispalyed | Found as per expectation | 123456 | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at the top navigation bar 3. Click on forgot password 4. Input valid user phone number 5. click on Submit button 6. Input a wrong OTP |  |  | Passed
30 |  |  |  | Verifying forgot password with a different phone number | It should display an error message | As expected | 1100547890 | 1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at the top navigation bar 3. Click on forgot password 4. Input invalid user phone number 5. click on Submit button |  |  | Passed
|  | Change Password | UI Testing | Checking whether the mandatory field are displaying | Mandatory fields should be displayed | As expected | N/A |  |  |  | Passed
|  |  |  | Checking whether the label texts are displayed | Should be displayed all label text above every input fields. | As expected | N/A |  |  |  | Passed
|  |  |  | Checking whether the update password button is clickable | The button should be clickable | As expected | N/A |  |  |  | Passed
|  |  | Functional testing | Checking whether the password fields are encripted or not | The password field should be encripted as per requirement | As expected | Current Password: 12345678 New Password: 12345678 Old Password: 12345678 | 1. Goto the URL https://publicmarket.com.bd/ 2. Login with valid phone number and password 3. Click on My profile 4. Scroll down 5. Type password in every field |  |  | Passed
|  |  |  | Verify the change password functionality by entering valid old password and matching new password and confirm password | [6 empty] | Not Executed
|  |  |  | Verify the funcionality by keeping old password field blank and entering new and confirm password | [6 empty] | Not Executed
|  |  |  | Verify the functionaity by leaving old,new and confirm password blank | [6 empty] | Not Executed
|  |  |  | Verify the functionaity by entering valid old password and entering unmatched new and confirm password | [6 empty] | Not Executed
|  |  |  | Verify the functionaity by entering valid old password and new password and leaving confirm password blank | [6 empty] | Not Executed
|  |  |  | Verify the change password functionality by entering invalid old password and matching new password and confirm password | [6 empty] | Not Executed
|  |  |  | Verify the confirmation message when the password has been updated | [6 empty] | Not Executed
Usuability Testing
|  | User Profile | UI Testing
Functional Testing
Usuability Testing
|  | Improvement Scopes |  | 'Remember Me' checkbox should be selected according to user
A maximum length of the password should be defined
Place 'Whats this?' below 'Remember Me'
Place 'Forgot your password' link below Password field
Negative test

## Bug Report
Bug Reporting
# SL 18
Issue: Password field has no maximum limit of characters
Reproducing Steps:
1. Goto the URL https://publicmarket.com.bd/ 2. Click on Login button at thetop navigation bar 3. Click on "New to PublicMarket" 4. Select the division and district 5. Input all the fields. 6. Input unlimited characters in password and Confirm password field 6. Enter Register button
Env: Production
Module: Sign Up
Severity: P1
Screenshot: Invalid email address error
Responsible QA: Nurul Afsar

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (62/62)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/62)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (54/62)*100 = 87.09
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (8/62)*100 = 12.90
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/62)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A